## Optimiza April 2018
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
Optimiza Planning | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Phase 1 | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
STO | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Analysis | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Investigations | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Investigate via error log and STO Open report | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Open report to be looked at to ensure no loopholes while changing hands | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Ops to share file for workaround investigation – work case examples | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Compile findings | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Development
Technical analysis
Development/Adjustments
Testing
Integration
IFT | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Analysis | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Investigations | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Compare Telkom/Oracle IFT report vs Optimiza data | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Ops to share issue examples including problem statements | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
“Composing” of IFT report to be investigated as per Melanie’s concern – Stewart shortened report | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Compile findings | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Development
Technical analysis
Development/Adjustments
Testing
Integration
PO | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Analysis | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Investigations | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Compare report and system data | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Compile findings | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Development | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Technical analysis | 25d | 2018-02-12 | 2018-03-16 |  |  | 100%
Development/Adjustments
Testing
Integration
Phase 1 testing
Phase 2
Recommended orders (MRP and DRP)
Analysis
Investigation
Compile findings
Development
Technical analysis
Development/Adjustments
Testing
Integration
Stock on Hand
Analysis
Investigation
Compile findings
Development
Technical analysis
Development/Adjustments
Testing
Integration
Previous Month History
Analysis
Investigation
Compile findings
Development
Technical analysis
Development/Adjustments
Testing
Integration
Month to date issues Extract
Analysis
Investigation
Compile findings
Development
Technical analysis
Development/Adjustments
Testing
Integration
Phase 2 testing
System testing